## project
Project Management Dashboard
Project Name: | [Name]
Report Date | [Date]
Project Status | On track
Completed | 77.78%
Tasks | Responsible | Priority | Status
Code test for hardware(1) | Huy | ★ | Complete
Analysis CAN log 28 | Khai |  | In progress
build sepuence download | Khai |  | In progress
coding response for ESP | Nghia |  | Complete
File doc for error frame | Huy |  | Complete
Add respond func to STM firmware | Nguyen |  | Complete
STM8 Unit Test | Nguyen |  | Complete
ESP Unit test | Nghia |  | Complete
Code test for hardware(2) | Hung |  | Complete
task name | name |  | 0%
task name | name |  | 0%
task name | name |  | 0%
task name | name |  | 0%
task name | name |  | 0%
task name | name |  | 0%
task name | name |  | 0%
Release | ALL

## data
Task Table |  | (mm/dd/yyy) | (mm/dd/yyy)
Tasks | Responsible | Start | End | Days | Status | Effort | Data Stype
Code test for hardware(1) | Huy | 2017-07-25 | 2017-07-31 | 6 | Complete | 4 | Complete
Analysis CAN log 28 | Khai | 2017-07-24 | 2017-07-25 | 1 | In progress | 1 | Overdue
build sepuence download | Khai | 2017-07-25 | 2017-07-26 | 1 | In progress |  | In progress
coding response for ESP | Nghia | 2017-07-25 | 2017-07-29 | 4 | Complete | 7 | Not started
File doc for error frame | Huy | 2017-07-25 | 2017-07-26 | 1 | Complete | 2
Add respond func to STM firmware | Nguyen | 2017-07-25 | 2017-07-29 | 4 | Complete | 7
STM8 Unit Test | Nguyen | 2017-08-02 | 2017-08-05 | 3 | Complete | 3
ESP Unit test | Nghia | 2017-08-02 | 2017-08-05 | 3 | Complete | 3
Code test for hardware(2) | Hung | 2017-07-25 | 2017-07-31 | 6 | Complete | 4
task name | name |  |  | 0
task name | name |  |  | 0
task name | name |  |  | 0
task name | name |  |  | 0
task name | name |  |  | 0
task name | name |  |  | 0
task name | name |  |  | 0
Release | ALL |  |  | 0
Percentage of Tasks Complete
Complete | 77.78%
Overdue | 0%
In progress | 22.22%
Not Started | 0%
Budget
Planned | 0
Actual | 0
Pending Items
Decisions | 0
Actions | 0
Change Requests | 0
Effort | Time (h)
Khai | 1
Huy | 2
Nguyen | 10
Nghia | 10
Hung | 4
0
0
0